## Sheet1
Date | TYPE | TODO | DoneDate
2018-10-19 | FEATURE | Scene change (main, space, planet, inner)
2018-10-19 | FEATURE | Various weapon
2018-10-19 | FEATURE | Space Battle
2018-10-19 | FEATURE | Main Menu in Main Scene | 2018-10-22
2018-10-19 | FEATURE | Main Menu in Game
2018-10-19 | FEATURE | Setting Menu
2018-10-19 | FEATURE | Save & Load
2018-10-19 | FEATURE | Fly to space & Landing on planet
2018-10-19 | FEATURE | Fly to space & Landing on Station
2018-10-19 | FEATURE | Transaction
2018-10-19 | FEATURE | Mission(protect something)
2018-10-19 | FEATURE | Mining resource on space
2018-10-19 | FEATURE | Mining resource on ground
2018-10-19 | FEATURE | Particle on main menu | 2018-10-19
2018-10-19 | FEATURE | Music on main menu | 2018-10-19
2018-10-19 | FEATURE | Space ship inventory
2018-10-19 | FEATURE | Transfer inventory & inventory
2018-10-19 | SCENE | Space_1 | 2018-10-22
2018-10-19 | SCENE | Space_2
2018-10-19 | SCENE | Space_3
2018-10-19 | SCENE | Other Base Station_1
2018-10-19 | SCENE | Other Base Station_2
2018-10-19 | SCENE | Other Base Station_3
2018-10-19 | SCRIPT | Mining Script
2018-10-19 | SCRIPT | Mission Script
2018-10-19 | SCRIPT | Ship Inventory Script
2018-10-19 | SCRIPT | Fly to space & Landing on planet Script
2018-10-19 | SCRIPT | Fly to space & Landing on Station Script
2018-10-19 | SCRIPT | Space Battle Script
2018-10-19 | SCRIPT | Main Menu in Main Scene Script
2018-10-19 | SCRIPT | Main Menu in Game Script
2018-10-19 | SCRIPT | Setting Menu Script
2018-10-19 | SCRIPT | Save & Load Script
2018-10-19 | SCRIPT | Transaction Script
2018-10-19 | SCRIPT | Transfer inventory & inventory Script
2018-10-19 | UI | Mining UI
2018-10-19 | UI | Mission UI
2018-10-19 | UI | Ship Inventory UI
2018-10-19 | UI | Fly to space & Landing on planet UI
2018-10-19 | UI | Fly to space & Landing on Station UI
2018-10-19 | UI | Space Battle UI
2018-10-19 | UI | Main Menu in Main Scene UI | 2018-10-22
2018-10-19 | UI | Main Menu in Game UI
2018-10-19 | UI | Setting Menu UI | 2018-10-22
2018-10-19 | UI | Save & Load UI
2018-10-19 | UI | Transaction UI
2018-10-19 | UI | Transfer inventory & inventory UI
2018-10-19 | ZETC | Get Assets | 2018-10-19
2018-10-19 | ZETC | Make Cockpit model with Asset
2018-10-20 | FEATURE | Random Gen Space
2018-10-20 | FEATURE | Player Base Station
2018-10-20 | FEATURE | Space Camera FPS
2018-10-20 | FEATURE | Space Camera TPS
2018-10-20 | SCENE
2018-10-20 | SCENE | Random Gen Space
2018-10-20 | SCENE | Player Base Station | 2018-10-22
2018-10-20 | SCRIPT | Scene change (main, space, planet, inner)
2018-10-20 | SCRIPT | Random Gen Space
2018-10-20 | SCRIPT | Player Base Station
2018-10-20 | SCRIPT | Plyaer info script
2018-10-20 | SCRIPT | Ship info script
2018-10-20 | UI
2018-10-20 | ZETC | Shader to mobile | 2018-10-20
2018-10-21 | SCENE | Planet_1
2018-10-21 | SCENE | Planet_2
2018-10-21 | SCENE | Planet_3
2018-10-21 | SCENE | Main Scene | 2018-10-22
2018-10-21 | SCRIPT | User Inventory
2018-10-21 | SCRIPT | User Status
2018-10-21 | SCRIPT | Player select & Ship select start
2018-10-21 | UI | User Ship Status
2018-10-21 | UI | Ship UI
2018-10-21 | UI | Person UI
2018-10-22 | UI | Continue UI | 2018-10-22
2018-10-22 | SCENE | Portal Prefab(Base, Left, Right) | 2018-10-22
2018-10-22 | SCRIPT | Inventory & Item Refactoring_1 | 2018-10-22
2018-10-22 | FEATURE | Premade Ship 1, 2 | 2018-10-22
2018-10-22 | FEATURE | Setting GamePlay
2018-10-22 | FEATURE | Setting Graphic
2018-10-22 | FEATURE | Setting Sound
2018-10-22 | FEATURE | Scene change[Main->NewGame] | 2018-10-23
2018-10-22 | FEATURE | Scene change[Main->LoadGame]
2018-10-22 | FEATURE | Scene change[Base -> Space]
2018-10-22 | FEATURE | Scene change[Space -> Base]
2018-10-22 | FEATURE | Scene change[Space -> Planet]
2018-10-22 | FEATURE | Scene change[Planet -> Space]
2018-10-22 | FEATURE | Scene Loading | 2018-10-23
2018-10-23 | FEATURE | ScreenShot from camera & use it | 2018-10-23
2018-10-23 | FEATURE | Make portal in/exit position | 2018-10-23
2018-10-23 | ZETC | How to play music ignoring audio source position | 2018-10-23
2018-10-21 | Object | PlayerShip 1 | 2018-10-21
2018-10-21 | Object | PlayerShip 2 | 2018-10-21
2018-10-23 | FEATURE
2018-10-25 | Animation | Player FPS Animation(shot, run, move) | 2018-10-25
2018-10-25 | Animation | Player TPS Anmation(need animator layer)
2018-10-25 | AC | Player FPS Anim Controller | 2018-10-25
2018-10-25 | AC | Player TPS Anim Controller | 2018-10-25
2018-10-26 | SCRIPT | Human input in Universe FPS
2018-10-26 | SCRIPT | Human input in Universe TPS
2018-10-26 | SCRIPT | Human input in Planet FPS | 2018-10-26
2018-10-26 | SCRIPT | Human input in Planet TPS | 2018-10-26
2018-10-26 | SCRIPT | Ship input in Planet FPS
2018-10-26 | SCRIPT | Ship input in Planet TPS
2018-10-26 | SCRIPT | Camera smooth with interpolation
2018-10-26 | SCRIPT | NewGame Chara, Ship Select
2018-10-26 | SCRIPT | NewGame Chara, Ship MouseOnUI